## Sheet1
PDR: | CDR: | FDR:
Team Definition | Schedule | Schedule
Vision & Mission | Update Roadmap | Update Roadmap
Team Roles | Update Gantt Chart | Update Gantt Chart
Project/Team Name | Update Charter
Company Name |  | Modeling
| Prototype Development | Update CAD
Schedule | Update Engineering Requirements and Constraints | Changes to Denervator
WBS | Finalize Design | Changes to Portal
Network Diagram | Validate Final Design with a Doctor | Back Stabilizer Ergonomic Improvements
Timelines | Identify Suitable Manufacturers | Changes to Stylet
| Create CAD Models | Create OP Sheets and Engineering DWGs
Problem Definition | Preliminary Prototype (Back Stabilizer)
Charter | CAD Portal | Fabrication
Problem Statement | CAD Stylet | Fabricate Stylet at ME Machine Shop
Patent Research (Google Patents) | CAD Denervator | Fabricate Portal at BIDC
SWOT Analysis | Create Assemblies | Print All PP Components at BIDC
Talk with a Doctor About SWOT |  | Fabricate Denervator at ME Machine Shop
Customer Analysis | Model Analysis | Assemble Prototype
Problem Verification | Select Industry-Grade Materials | Verify Basic Functionality and Iterate as Needed
X-ray Diffraction
Design | Biocompatibility | Testing
Customer Requirements | Sterilization | Rerun FEA and Iterate Design
Constraint Identification | Perform Analyses | Customer Needs Testing
Regulatory Environment Review | Thermal and Finite Element Analysis (FEA) | Force Testing
Engineering Specifications Chart | Stylet Tip and Nub | Modularity Testing
Validate ESC with a doctor | Denervator Tip | Customer Feedback
Perform Functional Decomposition (FD) | Handles/Bump Stop | Get Usage Feedback
Validate FD with a Doctor | Back Stabilizer Hinge Point | Verify Thoroughness of Testing
Concept Generation | Portal and C-Ring | Verify Feasibility of Procedure
Morphological Chart | Hand Calculations | Analyze Test Results and Iterate as Needed
Develop Preliminary Designs and Sketches | Clamping Friction on Portal Surface
Discuss Brainstorming with Doctor(s) | Fastener Analysis | Business Assignments
Perform Down Selection/Decision Matrix | Interpret Results and Refine Models as Necessary | Identify Standards
Refine Leading Design's Analysis Plan for CDR | Update Validation Plan | Update BOM
Identify Feasibility of Test Plans |  | Update Budget
Preliminary BOM and Sourcing Plan | Manufacturing Plan | Update all Other Business Sections as Needed
Update and Finalize BOM
Business Assignments | Discuss Mfg. Process with a Manufacturer | Report Deliverables
Risk Register | Finalize Process Flowcharts as Needed | Written Report
Preliminary Budget | Place Orders | Presentation
Value Proposition |  | Safety Review #3
Product Cost/Value | Business Assignments | Mallott Poster
Preliminary Pricing Analysis | Update Risk Register | Final Prototype Demo
Societal Benefit | FMEA
Gross Profit | Update Budget | Independent Work:
Market Segmentation | Update Value Proposition | Regulatory Compliance Testing
Market Size Estimation | Product Cost/Value | Perform Compliance Testing
Sales Quantity | Sales Quantity | Biocompatibility Tests
| Preliminary Pricing Analysis | Sterilization and Cleanliness Tests
Report Deliverables | Societal Benefit | Submit Documentation for Approval
Written Report | Gross Profit | Market Analysis
Presentation | Update Market Segmentation | Industry Analysis
Safety Review #1 | Update Market Size Estimation | PESTLE
Positioning Strategy
| Report Deliverables | Detailed Pricing Analysis
| Written Report | Sales Channels and Distribution Review
| Presentation | Marketing Strategy Development
| Safety Review #2 | Financial Projections